## Tabellenblatt1
Phase | Task | Description | Start | End | Duration | Responsibility | Participants | Resources
First Week | 1.1 - 1.4 Introduction, 2. Existing System | Research and Writing | 2020-05-09 | 2020-05-14 | 2h | Niklas | Yasmin, Luca | LaTeX, Requirements
First Week | 7.1-7.4, 8.1-8.3 Documentation of the Teamwork | Inserting the protocols and tables | 2020-05-08 | 2020-05-09 | 1h | Luca |  | LaTeX, Overleaf, protocols and Google Docs
First Week | 3.1 Overview of Requirements | Writing | 2020-05-09 | 2020-05-16 | 0,5h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.2 Functional Requirements | Add the previously defined requirements (check and format) | 2020-05-09 | 2020-05-16 | 1h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.3 Non-functional Requirements | Add the previously defined requirements (check and format) | 2020-05-09 | 2020-05-16 | 1h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.4 System Requirements | Writing Use cases | 2020-05-09 | 2020-05-12 | 6h | Sebastian | All | Requirements catalogue, client.pdf, client video
First Week | 3.4 System Requirements | Class model | 2020-05-09 | 2020-05-12 | 3h | Sebastian | All | Requirements catalogue, client.pdf, client video
First Week | UI Prototypes / Web UI Prototypes | Create prototypes for the Android App and Web App | 2020-05-09 | 2020-05-12 | 4h | Yasmin | Luca
Second Week | 5.1 Introduction | Writing | 2020-05-15 | 2020-05-19 | 3h | Johanna | Simon
Second Week | 5.2 Acceptance criteria | Work out methods to test the system | 2020-05-15 | 2020-05-19 | 3h | Johanna | Simon
Second Week | 6. System Tests | Work out methods to test the system | 2020-05-15 | 2020-05-19 | 4h | Yasmin | Sebastian, Niklas
Second Week | 4. Glossary | Writing and explaining | 2020-05-16 | 2020-05-19 | 1h | Luca | All | The finished text from the first week
Second Week | Compile and structure final Latex D1 document | Fixing errors and standardizing layout | 2020-05-19 | 2020-05-19 | 2h | Luca | All | LaTeX, Overleaf, the finished parts
Third Week | Reviewing D1 after we got feedback | Edit parts of the document to meet with the likings | 2020-05-28 | 2020-05-28 | 4h | Sebastian | All | LaTeX, Overleaf, D1, group feedback
Third Week | Write and read emails to and from the advisor | Writing E-Mails, communicating with Advisor and Client | 2020-05-20 | 2020-05-29 | 1h | Niklas | All | SoGO
Fourth Week | 1.1 Intention of system | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Niklas | All | LaTeX, Overleaf
Fourth Week | 1.2 Design goals | Writing | 2020-05-30 | 2020-06-01 | 1h | Johanna | All | LaTeX, Overleaf
Fourth Week | 1.3 Contradicting design goals | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Simon | All | LaTeX, Overleaf
Fourth Week | 1.4 Definitions, acronyms and abbreviations | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Sebastian | All | LaTeX, Overleaf
Fourth Week | 1.5 Literature references | Writing | 2020-05-30 | 2020-06-01 | - | Yasmin | All | LaTeX, Overleaf
Fourth Week | 1.6 Overview | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Luca | All | LaTeX, Overleaf
Fourth Week | 2 Existing system | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Luca | All | LaTeX, Overleaf
Fourth Week | 3.1 Overview | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Johanna | All | LaTeX, Overleaf
Fourth Week | 3.2 Component segmentation and description of interfaces | Writing and modelling | 2020-06-02 | 2020-06-05 | 4h | Sebastian | All | LaTeX, Overleaf, draw.io
Fourth Week | 3.3 Hardware/Software mapping | Writing and modelling | 2020-06-02 | 2020-06-05 | 1h | Yasmin | All | LaTeX, Overleaf, draw.io
Fourth Week | 3.4 Management of persistent data | Writing | 2020-06-02 | 2020-06-05 | 1h | Luca | All | LaTeX, Overleaf
Fourth Week | Refurbishing deliverable D1 | Refurbishing | 2020-05-30 | 2020-05-03 | 5h | Yasmin | All
Fifth Week | Refurbishing deliverable D1 | Refurbishing | 2020-05-04 | 2020-05-08 | 2h | Yasmin | All
Fifth Week | 3.5 Access rights and access control | Writing and elaborating | 2020-06-06 | 2020-06-11 | 1h | Luca | - | LaTeX, Overleaf
Fifth Week | 3.6 Global control flow | Writing, elaborating & modelling | 2020-06-06 | 2020-06-11 | 2h | Sebastian | Luca | LaTeX, Overleaf, draw.io
Fifth Week | 3.7 Boundary conditions | Writing and elaborating | 2020-06-06 | 2020-06-11 | 5h | Niklas | All | LaTeX, Overleaf
Fifth Week | 4 Glossary | Writing and explaining | 2020-06-06 | 2020-06-11 | 0.5h | Niklas | All | LaTeX, Overleaf
Fifth Week | II Documentation Of Group Work | Inserting the protocols and tables, Writing | 2020-06-06 | 2020-06-11 | 1h | Luca | Simon | LaTeX, Overleaf, protocols and Google Docs
Sixth Week | Refurbishing deliverable D2a | Refurbishing | 2020-06-15 | 2020-06-16 | 4h | Simon | All | LaTeX, Overleaf
Seventh Week | Awaiting feedback for D2a | Waiting | 2020-06-18 | 2020-06-25 | 1w | Niklas | All | Patience
Seventh Week | Final adjustments for D2a | Refurbishing | 2020-06-26 | 2020-06-26 | 2h | Simon | All | LaTeX, Overleaf
Seventh Week | Part II 1 Introduction | Writing and explaining | 2020-06-26 | 2020-06-26 | 1h | Sebastian | - | LaTeX, Overleaf
Seventh Week | Part II 2 Packages | Writing and modelling | 2020-06-24 | 2020-06-28 | 8h | Sebastian | All | LaTeX, Overleaf, draw.io
Eighth Week | Part II 3 Class interfaces | Writing and modelling | 2020-06-29 | 2020-07-06 | 8h | Simon | All | LaTeX, Overleaf
Eighth Week | Part IV Documentation of group work | Inserting the protocols and tables, Writing | 2020-06-29 | 2020-07-06 | 1h | Luca | All | LaTeX, Overleaf, protocols and Google Docs
Eighth Week | Firebase Testing/Integration | Coding and configuring | 2020-06-29 | 2020-07-06 | 9h | Luca | All | Android Studio, Firebase
Ninth Week | Part II 3 Class interfaces | Writing and modelling | 2020-07-06 | 2020-07-10 | 8h | Simon | All | LaTeX, Overleaf, Firebase, Android Studio
Ninth Week | Part III Integration Tests | Writing and explaining | 2020-07-08 | 2020-07-10 | 3h | Yasmin | All | LaTeX, Overleaf, Firebase, Android Studio
Ninth Week | Part II 4 Third-party Libraries, 5 Glossary | Writing | 2020-07-10 | 2020-07-10 | 0.5h | Johanna | All | LaTeX, Overleaf
Tenth Week | Awaiting feedback for D2b | Waiting | 2020-07-11 | 2020-07-17 | 1w | Sebastian | All | Patience
Eleventh Week | Awaiting feedback for D2b | Waiting | 2020-07-17 | 2020-07-21
Eleventh Week | Refurbishing deliverable D2b | Refurbishing | 2020-07-24 | 2020-07-24 | 3h | Niklas | All | LaTeX, Overleaf
Eleventh Week | Firebase: Setup | Researching and configuring | 2020-07-17 | 2020-07-24 | 1h | Sebastian | All | Firebase
Eleventh Week | Web App: Authentification | Coding | 2020-07-17 | 2020-07-24 | 2h | Luca | All | VS Code
Eleventh Week | Web App: Database/Settings | Coding | 2020-07-17 | 2020-07-24 | 7h | Luca | All | VS Code
Eleventh Week | Web App: Style | Coding | 2020-07-17 | 2020-07-24 | 2h | Luca | All | VS Code
Eleventh Week | Android App: Setup | Researching and configuring | 2020-07-17 | 2020-07-24 | 2h | Simon | All | Android Studio
Eleventh Week | Android App: Authentification | Coding | 2020-07-17 | 2020-07-24 | 2h | Simon | All | Android Studio
Twelfth Week | Android App: Mood recording process Part 1 | Coding | 2020-07-28 | 2020-07-29 | 6h | Simon | All | Android Studio
Twelfth Week | Android App: Mood recording process Part 2 (+ saving mood data to DB) | Coding | 2020-07-28 | 2020-07-29 | 4h | Niklas | All | Android Studio
Twelfth Week | Android App: Signup process (w/ consent form) | Coding | 2020-07-28 | 2020-07-30 | 9h | Johanna | All | Android Studio
Twelfth Week | Firebase: Cloudfunctions | Coding | 2020-07-28 | 2020-08-07 | 3h | Luca | All | VS Code
Twelfth Week | Android App: Questionnaires | Coding | 2020-07-30 | 2020-07-31 | 4h | Sebastian | All | Android Studio
Twelfth Week | Android App: Companions | Coding | 2020-07-30 | 2020-08-07 | 10h | Yasmin | All | Android Studio
Twelfth Week | Visualization (Android & Web) | Coding | 2020-07-30 | 2020-08-07 | 14h | Luca | All | Android Studio, VS Code
Twelfth Week | Android App: Notifications | Coding | 2020-08-02 | 2020-08-07 | 14h | Simon | All | Android Studio