## Tabellenblatt1
Phase | Task | Description | Start | End | Duration | Responsibility | Participants | Resources
First Week | 1.1-1.2 Introduction & Scope of the system | Research and Writing | 2020-05-09 | 2020-05-11 | 4h | Niklas | Yasmin | LaTeX, Requirements
First Week | 7.1-7.4, 8.1-8.3 Documentation of the Teamwork | Inserting the protocols and tables | 2020-05-08 | 2020-05-09 | 1h | Luca |  | LaTeX, Overleaf, protocols and Google Docs
First Week | 1.3 Goals and success criteria of the project | Writing | 2020-05-09 | 2020-05-11 | 2h | Niklas | Yasmin | LaTeX, Requirements
First Week | 1.4 Definitions, acronyms and abbreviations | Writing | 2020-05-09 | 2020-05-11 | 2h | Niklas | Luca,Yasmin | LaTeX, Requirements
First Week | 3.1 Overview of Requirements | Writing | 2020-05-09 | 2020-05-16 | 2h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.2 Functional Requirements | Add the previously defined requirements (check and format) | 2020-05-09 | 2020-05-16 | 2h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.3 Non-functional Requirements | Add the previously defined requirements (check and format) | 2020-05-09 | 2020-05-16 | 2h | Simon | Johanna | Requirements catalogue, client.pdf, client video
First Week | 3.4 System Requirements | Writing Use cases & Class model | 2020-05-09 | 2020-05-12 | 6h | Sebastian | All | Requirements catalogue, client.pdf, client video
Second Week | 5.1 Introduction | Writing | 2020-05-15 | 2020-05-20 | 3h | Johanna | Simon
Second Week | 5.2 Acceptance criteria | Work out methods to test the system | 2020-05-15 | 2020-05-20 | 3h | Johanna | Simon
Second Week | 6. System Tests | Work out methods to test the system | 2020-05-15 | 2020-05-21 | 4h | Yasmin | Sebastian, Niklas
Second Week | 4. Glossary | Writing and explaining | 2020-05-16 | 2020-06-05 | 3h | Luca | All | The finished text from the first week
Fourth Week | 1.1 Intention of system | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Niklas | All | LaTeX, Overleaf
Fourth Week | 1.2 Design goals | Writing | 2020-05-30 | 2020-06-01 | 1h | Yasmin | All | LaTeX, Overleaf
Fourth Week | 1.3 Contradicting design goals | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Simon | All | LaTeX, Overleaf
Fourth Week | 1.4 Definitions, acronyms and abbreviations | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Sebastian | All | LaTeX, Overleaf
Fourth Week | 1.5 Literature references | Writing | 2020-05-30 | 2020-06-01 | - | Yasmin | All | LaTeX, Overleaf
Fourth Week | 1.6 Overview | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Luca | All | LaTeX, Overleaf
Fourth Week | 2 Existing system | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Luca | All | LaTeX, Overleaf
Fourth Week | 3.1 Overview | Writing | 2020-05-30 | 2020-06-01 | 0.5h | Johanna | All | LaTeX, Overleaf
Fourth Week | 3.2 Component segmentation and description of interfaces | Writing and modelling | 2020-06-02 | 2020-06-05 | 6h | Sebastian | All | LaTeX, Overleaf, draw.io
Fourth Week | 3.3 Hardware/Software mapping | Writing and modelling | 2020-06-02 | 2020-06-05 | 1h | Yasmin | All | LaTeX, Overleaf, draw.io
Fourth Week | 3.4 Management of persistent data | Writing | 2020-06-02 | 2020-06-05 | 1h | Luca | All | LaTeX, Overleaf
Fifth Week | 3.5 Access rights and access control | Writing and elaborating | 2020-06-06 | 2020-06-11 | 1h | Sebastian | Yasmin | LaTeX, Overleaf
Fifth Week | 3.6 Global control flow | Writing, elaborating & modelling | 2020-06-06 | 2020-06-11 | 2h | Simon | Yasmin, Luca | LaTeX, Overleaf, draw.io
Fifth Week | 3.7 Boundary conditions | Writing and elaborating | 2020-06-06 | 2020-06-11 | 2h | Niklas | Johanna | LaTeX, Overleaf
Fifth Week | 4 Glossary | Writing and explaining | 2020-06-06 | 2020-06-11 | 0.5h | Niklas | All | LaTeX, Overleaf
Fifth Week | II Documentation Of Group Work | Inserting the protocols and tables, Writing | 2020-06-06 | 2020-06-11 | 1h | Luca | Simon | LaTeX, Overleaf, protocols and Google Docs
Seventh Week | Part II 1 Introduction | Writing and explaining | 2020-06-26 | 2020-06-26 | 1h | Sebastian | - | LaTeX, Overleaf
Seventh Week | Part II 2 Packages | Writing and modelling | 2020-06-24 | 2020-06-28 | 6h | Sebastian | All | LaTeX, Overleaf, draw.io
Eighth Week | Part II 3 Class interfaces | Writing and modelling | 2020-06-29 | 2020-07-06 | 3h | Simon | All | LaTeX, Overleaf
Eighth Week | Part III Integration Tests | Writing, explaining and modelling | 2020-06-29 | 2020-07-06 | 4h | Niklas | All | LaTeX, Overleaf
Eighth Week | Part IV Documentation of group work | Inserting the protocols and tables, Writing | 2020-06-29 | 2020-07-06 | 1h | Luca | All | LaTeX, Overleaf, protocols and Google Docs
Eighth Week | Firebase Testing/Integration | Coding and configuring | 2020-06-29 | 2020-07-06 | 3h | Luca | All | Android Studio, Firebase
Ninth Week | Part II 3 Class interfaces | Writing and modelling | 2020-07-06 | 2020-07-10 | 6h | Simon | All | LaTeX, Overleaf, Firebase, Android Studio
Ninth Week | Part III Integration Tests | Writing and explaining | 2020-07-08 | 2020-07-10 | 3h | Yasmin | All | LaTeX, Overleaf, Firebase, Android Studio
Ninth Week | Part II 4 Third-party Libraries, 5 Glossary | Writing | 2020-07-10 | 2020-07-10 | 0.5h | Johanna | All | LaTeX, Overleaf
Tenth Week | Awaiting Feedback, working on Feedback | Writing | 2020-07-10 | 2020-07-17 | 8h | Niklas | All | Latex, Overleaf, Firebase, Android Studio, Slack
Eleventh Week | Awaiting Feedback, working on Feedback | Writing | 2020-07-17 | 2020-07-24 | 5h | Sebastian | All | Latex, Overleaf, Firebase, Android Studio, Slack
Twelveth Week | Implementing the web interface | Coding | 2020-07-24 | 2020-07-28 | 10h | Luca | Simon
Twelveth Week | Implementing the android app | Coding | 2020-07-28 | 2020-08-02 | 20h | Johanna | All
Thirteenth Week | Implementing the android app | Coding | 2020-08-03 | 2020-08-09 | 40h | Yasmin | All
Fourteenth Week | Implementing the android app | Coding | 2020-08-10 | 2020-08-13 | 10h | Simon | All